## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Analyzing Student Data: Performance and Career Outcomes |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-2794
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 08-15-2024 | Project Scope Changes | Project Planning | Yes | Clearly define project objectives | Conducted regular project | Durgam Devani | SOLVED | NA
2 | 2024-05-08 | Data Collection Issues | Data Collection | Yes | Develop a data collection plan | Implemented data validation process to clean data. | Durgam Devani | SOLVED | NA