## Sheet1
GENERAL PROJECT INFORMATION
PROJECT NAME: | Analyzing Student Data: Performance and Career Outcomes
PROJECT SPONSOR: | Tushar Topale
PROJECT MANAGER: | Harshada Topale
EXPECTED START DATE: | 01-06-2024(MMDDYYYY)
EXPECTED COMPLETION DATE: | 30-08-2024(MMDDYYYY)
ESTIMATED COST: | NA
GOALS,OBJECTIVES,DELVERABLES
PROJECT OBJECTIVE: | We're analyzing our intern students' academic performance, event participation, career aspirations, and success factors using a dataset containing various attributes.
BUSINESS CASE: | The business case aims to enhance student interns' success and program improvement by examining academic performance, event attendance, and career goals.
GOALS/METRICS: | The goal is to assist students in identifying areas where they need to enhance their skills and qualifications to secure expected salaries and jobs.
EXPECTED DELIVERABLES: | The report includes an EDA, regression analysis, visualizations, recommendations, dashboard, documentation, and raw data file, providing valuable insights into student intern success and program improvement.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE: | The study analyzes data to identify connections between academic performance, event attendance, and job goals, focusing on factors influencing student intern success. The findings will inform future research and improve the internship program.
OUTSIDE OF SCOPE: | The analysis will provide actionable recommendations for optimizing the internship program, identifying links between academic performance, event attendance, and job goals, and investigating factors influencing student intern success. The deliverables will include data visualizations, recommendations, and documentation.
PROJECT RESOURCES AND COSTS
PROJECT TEAM: | Durgam Devani (Intern)
SUPPORT RESOURCES: | PowerBI/Tabuelo/MS Excel- The data analysis team, including data infrastructure experts, subject matter experts, project management, stakeholder engagement, presentation, budget allocation, and ethical compliance, will provide actionable recommendations to optimize the internship program. The analysis will identify links between academic performance, event attendance, and job goals, and investigate elements influencing student intern success. The team will produce data preprocessing reports, exploratory data analysis, regression analysis, data visualizations, recommendations, presentations, data insights dashboards, documentation, future research opportunities, and raw data files.
COST ALLOCATION: | 0-As their is no platform fee
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER: | Harshada Topale
KEY STAKEHOLDERS: | Harshada Topale
END CUSTOMERS: | Cloud Counselage Pvt. Ltd.
PROJECT RISKS,CONSTRAINTS,ASSUMPTIONS
RISKS: | The relationship between a student's economic background, academic success, competency, and predicted wage is not well understood. Data may not be cleaned or processed.
ASSUMPTIONS: | Data accuracy, completeness, representativeness, confidentiality, event participation impact, career aspirations accuracy, Academic performance measures, No sample bias, no confounding variables, Time period, generalizability, continuous improvement (list of points)
CONSTRAINTS: | The study faces challenges such as limited data size, time constraints, ethical considerations, external factors, resource limitations, causal inference, generalizability, interpretation, incomplete attribute coverage, retrospective analysis, and recommendations scope.
MILESTONES
MILESTONE 1-REQUIREMENT GATHERING: | 2024-06-05
MILESTONE 2-PLANNING: | 2024-06-10
MILESTONE 3-DESIGN: | 2024-07-05
MILSTONE 4-DEVELOPMENT: | 2024-08-05
MILSTONE 5-TESTING: | 2024-08-18
MILSTONE 6-DELPOYMENT: | 2024-08-22
MILSTONE 7-CLOSURE: | 2024-08-29